## Prime partner RACI
| Client | Partner | Redpoint Services | Comment | Task descriptions and comments
Discovery
Workshop agendas | I | R | C
Workshop scheduling | A | R
Workshop delivery | C | R | C
Data model | I | R | C |  | Task: Redpoint session to share Redpoint's data model design philosophy
Environment design and sizing | R | R | C | Dependent on who is hosting | Comment: Dependent on which party is hosting
Documentation | I | R | C
Implementation plan | R | R | C
Implementation
Project management | R | R | I |  | Task: Redpoint session to share Redpoint's delivery methdology and validation steps
Technical leadership | C | R | C
Provision environment and database | R | R | I | Dependent on who is hosting | Comment: Dependent on which party is hosting
Install software | I | C | R |  | Pre-requisites: Environment provisioned by client or partner, with network access. Task: Install Redpoint software and establish connectivity to database etc
Request and provide licenses for boxes | I | R | R |  | Pre-requisite: Redpoint software installed. Task: Request licence for Redpoint Licencing and apply licence to environment
Redpoint Data Management (RPDM)
RPDM ingestion processes | C | R | I |  | Task: Redpoint session to share Redpoint's ETL strategies for loading data
RPDM outbound processes | C | R | I
Matching (First project for partner) | A | C | R |  | Pre-requisite: Access to a significant amount of production quality customer data. Task: Iterative matching workshops where customer data is passed through the Redpoint matching engine and under/over matching is adjusted until all parties agree on the match.
Matching (ongoing projects for partner) | C | R | I
Golden record and aggregates | C | R | I
Core Software User training | C | I | R |  | Task: Training on Redpoint products
Solution Specific Training | C | R | C
Redpoint Interaction (RPI)
RPI attributes and config | I | R | C |  | Comment: Redpoint moves to I for experienced partners
Core Software User training | C | I | R |  | Task: Training on Redpoint products
Solution Specific Training | C | R | C
Initial campaigns | R | R | C
Real Time Decisions
Configuration (First project for partner) | I | C | R | RP is prescriptive based on articulated requirements | Task: Set up Realtime decisions on behalf of new partners
Configuration (Ongoing projects for partner) | C | R | I |  | Comment: Partner is responsible with active input from knowledgeable Client
Initial campaigns | R | R | C
Acceptance and Go-live
UAT plan | R | C | I
UAT support | C | R | I
UAT delivery | R | C | I
Go-live checklist | I | R | C
Support and BAU
Account management | C | R | I
Support handover |  | R | C
Database maintenance | R | R | C
Environment monitoring | R | R | C
First level support |  | R | I
Second level support |  | I | R
Ongoing campaign support | C | R
Data changes | C | R | I
Change Management | C | R | I
R Responsible A Accountable C Consulted I Informed